## Sheet1
*Note Change the values for D5 to F9 only | The rest of the values are computed by the formula |  | The password for unlocking the sheet is 123
BURNDOWN CHART GROUP01 C2
Task | Category | Total Number of Task per Category | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Usecase and Testcase Creation | Diagram | 2 | 2 | 0 | 0 | 0 | 0 | 0
System Functionalities | Program | 7 | 3 | 0 | 0 | 0 | 4
Account Authentications with Database | DBS | 4 | 0 | 0 | 0 | 0 | 4
Creation of GUI | GUI | 24 | 10 | 0 | 0 | 0 | 14
Software Debugging | Testing | 4 | 1 | 0 | 0 | 0 | 3
|  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Actual Effort |  | 41 | 25 | 25 | 25 | 25
Ideal Effort |  | 41 | 30 | 20 | 10 | 0
TASKS
Use Case and Test Case Creation |  | UseCase
Test Case
System Functionalities |  | Open Account
Close Account
View Account
Admin Login
View Account Search
Account Authentication |  | Admin Authentication
Client Authentication
Creation of GUI |  | Login Page
Home Page
Close Account Page
Open Account Page
View Info Page
Warning and Error Messages (5)
Software Debugging |  | Error Checking (7)